## Issues and Resolutions
# | Issue Date | Issue | Resolve Notes | Resolved Date | Status
1 | 2026-07-06 | Platform needed live Snowflake/DQ/task monitoring with RCA to Fix to Validate flow | Built FastAPI agents + React UI + Snowflake/AWS/DQ/lineage connectors (initial commits 08ab91b / 6f20d76) | 2026-07-06 | Done
2 | 2026-07-07 | RCA was thin / hard to trust (little evidence, weak lineage) | Added dynamic lineage, DQ evidence collection, SQL guardrail, richer RCA skill/knowledge (0f699e8) | 2026-07-07 | Done
3 | 2026-07-10 | RCA narrative not operator-friendly | Added RichRootCause, Workbench polish, learnings/patterns memory, chat/session improvements (f9201d1) | 2026-07-10 | Done
4 | 2026-07-19 | Real DQ failures (e.g. QC 303 Kerendia L3/L2 cardinality) exposed weak evidence cite and vague root cause | Deeper DQ diagnostics; evidence cite for short counts; deterministic L3/L2 cardinality RC; promote code_analysis when it cites evidence (landed in dfea219) | 2026-08-11 | Done
5 | 2026-08-11 | Long DQ SQL hit Snowflake client timeout (000604); timeouts treated like data FAIL | Raised network_timeout 60s to 600s; timeout treated as inconclusive (not confirmed FAIL); RCA messaging for timeouts | 2026-08-11 | Done
6 | 2026-08-11 | Fix Agent invented ETL objects / used hardcoded category templates; Before/After not SQL-only | RCA-only seeding; prefer procedure_chain SQL; invent-object guards; reject bad LLM polish; SQL-only Before/After (01f4783) | 2026-08-13 | Done
7 | 2026-08-13 | DQ RCA with no failed task left Fix without writer procedure SQL | Added resolve_writer_procedures_for_tables(); RCA resolves writers from failing tables | 2026-08-13 | Done
8 | 2026-08-13 | No place to browse / add RCA knowledge from UI | Added Knowledge tab + Workbench Add / View Knowledge | 2026-08-13 | Done
9 | 2026-08-21 | Chat / packaging gaps for demo and deploy | Chat agent upgrades; Dockerfile + docker-compose (0012e9c) | 2026-08-21 | Done
10 | 2026-08-25 | Lineage / Dashboard UX needed polish | Lineage graph updates, Dashboard/Workbench RCA flow, skills/knowledge tweaks (59bc63c, 2501636) | 2026-08-27 | Done
11 | 2026-08-25 | Need AWS ECS / Fargate deployment path | Added deploy/ecs pack (task definition, secrets example, README) | 2026-08-25 | Done (local)
12 | 2026-09-02 | Auth only Password/SSO; key-pair needed | Key-pair / JWT auth in config, connector, Settings, connectivity hints |  | In progress (uncommitted)
13 | 2026-09-02 | Dashboard TASK_HISTORY could hang up to full 600s network timeout | Separate telemetry STATEMENT_TIMEOUT (~60s) so summary does not block on long history scans |  | In progress (uncommitted)
14 | 2026-08-11 | Evidence-based SQL backtracking RCA (step replay) not implemented | Spec in conversation.txt; stubs only (rca_trace.py, test_rca_agent_backtrack.py) — framework not coded yet |  | Open
15 | 2026-09-03 | Test connections checked only already-saved credentials; no success popup and no option to save after a successful test | Test now probes current form values (POST /api/connectivity, no save). Success popup offers Save connections; failure popup shows detail. GET /api/connectivity kept for page-load saved status | 2026-09-03 | Done
16 | 2026-09-03 | Save connections API looked broken after Test — Save returned OK but then forced another SSO/browser login via post-save connectivity re-check and always reset the shared Snowflake session | Save no longer resets the shared session when connection credentials are unchanged. Modal Save keeps the successful Test result and does not re-call GET /connectivity (avoids second SSO). | 2026-09-03 | Done
17 | 2026-08-11 | RCA / Dashboard needed clear upstream and downstream lineage so operators can see impact paths | Integrated upstream and downstream lineage into the RCA Dashboard / Workbench views (lineage graphs and table lineage) so RCA shows source-to-impact flow | 2026-08-27 | Done
18 | 2026-08-11 | Dashboard / RCA views were hard to narrow for large task and DQ result sets | Enabled filtering functionality on the Dashboard (status / date range and related filters) so operators can focus failed or relevant runs | 2026-08-27 | Done